## Work Log
CSIS 4495 - Applied Research Project
Work Log - Desmond Chua (300369803)
BC Personal Health Management Platform
Date | Sprint | Duration | Hours | Category | Task ID | Description of Work Done
2026-01-09 | 0 | 2 hr | 2 | 0: Environment Setup |  | Attended CSIS 4495 class; reviewed project requirements; brainstormed initial ideas based on Richmond Hospital experience
2026-01-09 | 0 | 1.5 hr | 1.5 | 0: Environment Setup |  | Researched BC healthcare navigation tools; identified gap in existing solutions
2026-01-15 | 0 | 2 hr | 2 | Learning & Research |  | Drafted initial chatbot concept; researched CTAS triage guidelines
2026-01-16 | 0 | 1 hr | 1 | 0: Environment Setup |  | Meeting #1 with instructor; received feedback to broaden scope; began expanding to multi-feature platform
2026-01-17 | 0 | 2.5 hr | 2.5 | Learning & Research |  | Researched OpenAI API documentation; explored integration options
2026-01-18 | 0 | 2 hr | 2 | 0: Environment Setup |  | Meeting #2 with instructor (virtual); Option 1 approved; received guidance on focus areas
2026-01-19 | 0 | 3 hr | 3 | Learning & Research |  | Designed hybrid classification approach; researched Kaggle symptom datasets
2026-01-20 | 0 | 2.5 hr | 2.5 | 0: Environment Setup |  | Created GitHub repository; set up project structure
2026-01-21 | 0 | 3 hr | 3 | Learning & Research |  | Researched ML analytics techniques for dashboards; planned Power BI integration
2026-01-22 | 0 | 2.5 hr | 2.5 | Learning & Research |  | Explored synthetic data generation approaches; documented data strategy
2026-01-23 | 0 | 3 hr | 3 | 6: Documentation + Submission |  | Drafted proposal introduction and literature review sections
2026-01-24 | 0 | 3.5 hr | 3.5 | 6: Documentation + Submission |  | Completed methodology section; created technical architecture diagram
2026-01-30 | 0 | 15 min | 0.25 | 0: Environment Setup | 0.1 | Install Python 3.13+ and verify installation
2026-01-30 | 0 | 15 min | 0.25 | 0: Environment Setup | 0.2 | Install Visual Studio Code with Claude Code extension
2026-01-30 | 0 | 15 min | 0.25 | 0: Environment Setup | 0.3 | Create GitHub repo (W26_4495_S2_DesmondC); set up folder structure; add instructor as collaborator
2026-01-30 | 0 | 15 min | 0.25 | 0: Environment Setup | 0.4a | Create OpenAI account; add $5 API credit
2026-01-30 | 0 | 5 min | 0.1 | 0: Environment Setup | 0.4b | Create OpenAI API key (BC-Health-Platform)
2026-01-30 | 0 | 1 hr | 1 | 0: Environment Setup |  | Attended CSIS 4495 Lesson 4 class; individual check-in with instructor; received feedback on project approach
2026-01-30 | 0 | 10 min | 0.17 | 0: Environment Setup | 0.5 | Created Streamlit Cloud account; connected with GitHub for deployment
2026-01-30 | 0 | 5 min | 0.08 | 0: Environment Setup | 0.6 | Created Python virtual environment (venv) for isolated project dependencies
2026-01-30 | 0 | 15 min | 0.25 | 0: Environment Setup | 0.7 | Installed packages: streamlit, openai, pandas, scikit-learn, plotly, folium, python-dotenv, numpy, nltk, sqlalchemy, spacy
2026-01-30 | 0 | 5 min | 0.08 | 0: Environment Setup | 0.8 | Ran 'streamlit hello' to verify Streamlit installation; demo app loaded successfully at localhost:8501
2026-01-30 | 0 | 10 min | 0.17 | 0: Environment Setup | 0.9 | Created requirements.txt using pip freeze; removed spacy model reference for clean deployment
2026-01-31 | 1 | 25 min | 0.42 | Learning & Research | L2 | Udemy Streamlit ML Deployment - Lesson 2: Installation and Setup (virtual environments, Python 3.8-3.12, streamlit hello)
2026-01-31 | 1 | 35 min | 0.58 | Learning & Research | L3 | Udemy Streamlit ML Deployment - Lesson 3: Overview of Streamlit (data flow concept, caching preview, key features)
2026-01-31 | 1 | 30 min | 0.5 | Learning & Research | L4 | Udemy Streamlit ML Deployment - Lesson 4: Creating Basic Streamlit App (main.py, st.text, auto-reload workflow)
2026-02-01 | 1 | 15 min | 0.25 | Learning & Research | L5 | Udemy Streamlit ML Deployment - Lesson 5: Text Elements (st.title, st.header, st.markdown, st.code, st.latex)
2026-02-01 | 1 | 20 min | 0.33 | Learning & Research | L6 | Udemy Streamlit ML Deployment - Lesson 6: Data Display Elements (st.dataframe, st.table, st.metric for KPIs)
2026-02-01 | 1 | 20 min | 0.33 | Learning & Research | L7 | Udemy Streamlit ML Deployment - Lesson 7: Charting Elements (st.line_chart, st.bar_chart, st.area_chart, st.map)
2026-02-01 | 1 | 25 min | 0.42 | Learning & Research | L8-9 | Udemy Streamlit ML Deployment - Lessons 8-9: Input Widgets (st.button, st.checkbox, st.radio, st.selectbox, st.slider)
2026-02-01 | 1 | 15 min | 0.25 | Learning & Research | L10 | Udemy Streamlit ML Deployment - Lesson 10: Forms (st.form, form_submit_button, batch submissions)
2026-02-01 | 1 | 15 min | 0.25 | Learning & Research | L11 | Udemy Streamlit ML Deployment - Lesson 11: Layout Elements (st.sidebar, st.columns, st.tabs, st.expander)
2026-02-01 | 1 | 40 min | 0.67 | Learning & Research | L12-13 | Udemy Streamlit ML Deployment - Lessons 12-13: Capstone (Canada unemployment dashboard with forms, tabs, metrics, matplotlib)
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.1 | Create Mockup 1a - Login page design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.2 | Create Mockup 1b - Register page with health profile using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.3 | Create Mockup 2a - Home Dashboard design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.4 | Create Mockup 2b - Facility Finder page design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.5 | Create Mockup 2c - Health Library page design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.6 | Create Mockup 3 - Chatbot Interface design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.7 | Create Mockup 4 - My Dashboard (Personal) design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.8 | Create Mockup 5 - System Analytics page design using UX Pilot
2026-02-01 | Sprint 1 | 10 min | 0.17 | 1A: UI Mockups | 1A.9 | Organize all mockup files in Misc/design/ folder
2026-02-01 | Sprint 1 | 15 min | 0.25 | 1B: Project Structure | 1B.1 | Create folder structure (src/, pages/, components/, .streamlit/, data/)
2026-02-01 | Sprint 1 | 10 min | 0.17 | 1B: Project Structure | 1B.2 | Create .streamlit/config.toml with VCH theme colors (teal #006271, blue #0078AE)
2026-02-01 | Sprint 1 | 15 min | 0.25 | 1B: Project Structure | 1B.3 | Create empty placeholder files for all pages
2026-02-02 | Sprint 1 | 30 min | 0.5 | 1C: Database Setup | 1C.1 | Create components/database.py - Initialize SQLite database module using Claude Code
2026-02-02 | Sprint 1 | 30 min | 0.5 | 1C: Database Setup | 1C.2 | Create users table schema (id, name, email, password_hash, age, gender, region, health_conditions)
2026-02-02 | Sprint 1 | 30 min | 0.5 | 1C: Database Setup | 1C.3 | Create assessments table schema (id, user_id, symptoms, extracted_symptoms, urgency_level, recommendation)
2026-02-02 | Sprint 1 | 45 min | 0.75 | 1C: Database Setup | 1C.4 | Implement user CRUD functions (create_user, get_user_by_email, get_user_by_id, update_user, verify_user_exists)
2026-02-02 | Sprint 1 | 30 min | 0.5 | 1C: Database Setup | 1C.5 | Implement assessment CRUD functions (save_assessment, get_user_assessments, get_assessment_by_id, get_assessment_stats)
2026-02-02 | Sprint 1 | 20 min | 0.33 | 1C: Database Setup | 1C.6 | Test database with dummy data; Install SQLite Viewer VS Code extension; Verify tables
2026-02-02 | Sprint 1 | 5 min | 0.1 | 1C: Database Setup | 1C.7 | Git commit and push: 'Sprint 1C complete: Database setup with users and assessments tables'
2026-02-04 | Sprint 1 | 45 min | 0.75 | 1D: Authentication Feature | 1D.1 | Create components/auth.py (hash_password, verify_password functions using bcrypt)
2026-02-04 | Sprint 1 | 1 hr | 1 | 1D: Authentication Feature | 1D.2 | Create app.py with Login tab UI (email, password, remember me checkbox)
2026-02-04 | Sprint 1 | 1.5 hr | 1.5 | 1D: Authentication Feature | 1D.3 | Create app.py with Register tab UI (name, email, password, health profile, 10 health conditions)
2026-02-04 | Sprint 1 | 45 min | 0.75 | 1D: Authentication Feature | 1D.4 | Implement login logic (verify credentials, set session_state)
2026-02-05 | Sprint 1 | 45 min | 0.75 | 1D: Authentication Feature | 1D.5 | Implement register logic (validate, hash password, save to DB)
2026-02-05 | Sprint 1 | 15 min | 0.25 | 1D: Authentication Feature | 1D.6 | Add logout functionality (clear session and redirect to login)
2026-02-05 | Sprint 1 | 30 min | 0.5 | 1D: Authentication Feature | 1D.7 | Protect pages (redirect to login if not authenticated)
2026-02-05 | Sprint 1 | 30 min | 0.5 | 1D: Authentication Feature | 1D.8 | Test login/register/logout flow (9 test cases: registration, duplicate email, password/email validation, wrong password, logout, page protection, database verification); Clean up orphaned test data
2026-02-05 | Sprint 1 | 30 min | 0.5 | 1E: Basic Navigation | 1E.1 | Create pages/1_🏠_Home.py with welcome message
2026-02-05 | Sprint 1 | 10 min | 0.17 | 1E: Basic Navigation | 1E.2 | Create pages/2_💬_Symptom_Assessment.py (placeholder)
2026-02-05 | Sprint 1 | 10 min | 0.17 | 1E: Basic Navigation | 1E.3 | Create pages/3_📊_My_Dashboard.py (placeholder)
2026-02-05 | Sprint 1 | 10 min | 0.17 | 1E: Basic Navigation | 1E.4 | Create pages/4_🗺️_Facility_Finder.py (placeholder)
2026-02-05 | Sprint 1 | 10 min | 0.17 | 1E: Basic Navigation | 1E.5 | Create pages/5_📚_Health_Library.py (placeholder)
2026-02-05 | Sprint 1 | 10 min | 0.17 | 1E: Basic Navigation | 1E.6 | Create pages/6_📈_System_Analytics.py (placeholder)
2026-02-05 | Sprint 1 | 15 min | 0.25 | 1E: Basic Navigation | 1E.7 | Test navigation between all pages; Verify sidebar navigation works; Git commit and push
TOTAL HOURS |  |  |  | 49.61

## Dashboard
PROJECT PROGRESS DASHBOARD
SPRINT PROGRESS SUMMARY
Sprint | Phase Name | Target Hours | Actual Hours | % Complete
0 | Environment Setup | 5 | 11.85 | 100%
1 | Basic App Structure | 15 | 14.26 | 95.07%
2 | Symptom Chatbot | 25 | 0 | 0%
3 | Features 3A-3D | 20 | 0 | 0%
4 | System Analytics | 20 | 0 | 0%
5 | Deployment & Testing | 15 | 0 | 0%
6 | Documentation + Submission | 18 | 6.5 | 36.11%
TOTAL |  | 118 | 32.61 | 27.64%
GANTT CHART - PROJECT TIMELINE
Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
| Jan 27 | Feb 3 | Feb 10 | Feb 17 | Feb 24 | Mar 3 | Mar 10 | Mar 17 | Mar 24 | Mar 31 | Apr 7 | Apr 14 | Apr 21
Sprint 0: Environment Setup | bar: Jan 27 to Feb 3
Sprint 1: Basic App Structure | bar: Jan 27 to Feb 10
1A: UI Mockups | bar: Feb 3 to Feb 17
1B: Project Structure | bar: Feb 3 to Feb 10
1C: Database Setup | bar: Feb 3 to Feb 17
1D: Authentication Feature | bar: Feb 3 to Feb 17
1E: Basic Navigation | bar: Feb 10; Feb 24 to Mar 3
Sprint 2: Symptom Chatbot | bar: Feb 10 to Feb 24
2A: Open AI Integration | bar: Feb 10 to Mar 3
2B: Safety Layer - CTAS Rules | bar: Feb 17; Mar 3
2C: ML Model Training | bar: Feb 17 to Feb 24; Mar 10 to Mar 17
2D: Chatbot UI + Integration | bar: Feb 24; Mar 10
Sprint 3: Features 3A-3D | bar: Feb 24 to Mar 17
3A: Home Dashboard | bar: Feb 24 to Mar 3; Mar 17
3B: My Dashboard - Personal Analytics | bar: Mar 3; Mar 24 to Mar 31
3C: Facility Finder | bar: Mar 3 to Mar 10; Mar 24
3D: Health Education Library | bar: Mar 10; Mar 24 to Mar 31
Sprint 4: System Analytics | bar: Mar 10 to Mar 31
4A: System Analytics Data | bar: Feb 24; Mar 10 to Mar 17
4B: System Analytics Dashboard | bar: Mar 17 to Mar 24; Apr 21
Sprint 5: Deployment & Testing | bar: Mar 24 to Apr 7
5A: Deployment | bar: Mar 24 to Mar 31
5B: Testing | bar: Mar 31 to Apr 7
Sprint 6: Documentation | bar: Apr 7 to Apr 21
Category | Jan 27: Hours
HOURS BY CATEGORY
Category | Jan 27: Hours
0: Environment Setup | Jan 27: 11.85
1A: UI Mockups | Jan 27: 2.81
1B: Project Structure | Jan 27: 0.67
1C: Database Setup | Jan 27: 3.18
1D: Authentication Feature | Jan 27: 6
1E: Basic Navigation | Jan 27: 1.6
2A: Open AI Integration | Jan 27: 0
2B: Safety Layer - CTAS Rules | Jan 27: 0
2C: ML Model Training | Jan 27: 0
2D: Chatbot UI + Integration | Jan 27: 0
3A: Home Dashboard | Jan 27: 0
3B: My Dashboard - Personal Analytics | Jan 27: 0
3C: Facility Finder | Jan 27: 0
3D: Health Education Library | Jan 27: 0
4A: System Analytics Data | Jan 27: 0
4B: System Analytics Dashboard | Jan 27: 0
5A: Deployment | Jan 27: 0
5B: Testing | Jan 27: 0
6: Documentation + Submission | Jan 27: 6.5
Learning & Research | Jan 27: 17
Proof of Concept | Jan 27: 0
TOTAL | Jan 27: 49.61

## Categories
Category Reference
Category | Sprint | Description
0: Environment Setup | 0 | Python, VS Code, GitHub, OpenAI API, Streamlit Cloud setup
1A: UI Mockups | 1 | Create UI mockups for all pages using UX Pilot
1B: Project Structure | 1 | Create folder structure, config.toml, placeholder files
1C: Database Setup | 1 | SQLite database, users/assessments tables, CRUD functions
1D: Authentication Feature | 1 | Login, register, logout, session management with bcrypt
1E: Basic Navigation | 1 | Multi-page navigation, sidebar, page routing
2A: Open AI Integration | 2 | OpenAI API setup, symptom extraction prompts
2B: Safety Layer - CTAS Rules | 2 | Rule-based critical symptom detection (CTAS guidelines)
2C: ML Model Training | 2 | Kaggle data, Random Forest training, model.pkl
2D: Chatbot UI + Integration | 2 | Chat interface, session state, urgency display, integration
3A: Home Dashboard | 3 | Home page with welcome message, quick stats, navigation cards
3B: My Dashboard - Personal Analytics | 3
3C: Facility Finder | 3 | BC facilities data, Folium map, filters by region/type
3D: Health Education Library | 3 | Health topics JSON, search, topic cards, resources
4A: System Analytics Data | 4 | Generate 5000 synthetic records, seasonal patterns
4B: System Analytics Dashboard | 4 | K-Means clustering, anomaly detection, forecasting
5A: Deployment | 5 | Streamlit Cloud deployment, secrets config, live testing
5B: Testing | 5 | Test scenarios, user feedback, edge cases, disclaimers
6: Documentation + Submission | 6 | Final report, demo video, presentation, submission
Learning & Research | - | Udemy courses, tutorials, documentation, self-study
Proof of Concept | - | Code experiments, feature demos, testing feasibility