## Work Log
CSIS 4495 - Applied Research Project
Work Log - Desmond Chua (300369803)
BC Personal Health Management Platform
Date | Sprint | Duration | Hours | Category | Task ID | Description of Work Done
2026-01-09 | 0 | 2 hr | 2 | 0: Environment Setup |  | Attended CSIS 4495 class; reviewed project requirements; brainstormed initial ideas based on Richmond Hospital experience
2026-01-09 | 0 | 1.5 hr | 1.5 | 0: Environment Setup |  | Researched BC healthcare navigation tools; identified gap in existing solutions
2026-01-15 | 0 | 2 hr | 2 | Learning & Research |  | Drafted initial chatbot concept; researched CTAS triage guidelines
2026-01-16 | 0 | 1 hr | 1 | 0: Environment Setup |  | Meeting #1 with instructor; received feedback to broaden scope; began expanding to multi-feature platform
2026-01-17 | 0 | 2.5 hr | 2.5 | Learning & Research |  | Researched OpenAI API documentation; explored integration options
2026-01-18 | 0 | 2 hr | 2 | 0: Environment Setup |  | Meeting #2 with instructor (virtual); Option 1 approved; received guidance on focus areas
2026-01-19 | 0 | 3 hr | 3 | Learning & Research |  | Designed hybrid classification approach; researched Kaggle symptom datasets
2026-01-20 | 0 | 2.5 hr | 2.5 | 0: Environment Setup |  | Created GitHub repository; set up project structure
2026-01-21 | 0 | 3 hr | 3 | Learning & Research |  | Researched ML analytics techniques for dashboards; planned Power BI integration
2026-01-22 | 0 | 2.5 hr | 2.5 | Learning & Research |  | Explored synthetic data generation approaches; documented data strategy
2026-01-23 | 0 | 3 hr | 3 | 6: Documentation + Submission |  | Drafted proposal introduction and literature review sections
2026-01-24 | 0 | 3.5 hr | 3.5 | 6: Documentation + Submission |  | Completed methodology section; created technical architecture diagram
2026-01-30 | 0 | 15 min | 0.25 | 0: Environment Setup | 0.1 | Install Python 3.13+ and verify installation
2026-01-30 | 0 | 15 min | 0.25 | 0: Environment Setup | 0.2 | Install Visual Studio Code with Claude Code extension
2026-01-30 | 0 | 15 min | 0.25 | 0: Environment Setup | 0.3 | Create GitHub repo (W26_4495_S2_DesmondC); set up folder structure; add instructor as collaborator
2026-01-30 | 0 | 15 min | 0.25 | 0: Environment Setup | 0.4a | Create OpenAI account; add $5 API credit
2026-01-30 | 0 | 5 min | 0.1 | 0: Environment Setup | 0.4b | Create OpenAI API key (BC-Health-Platform)
2026-01-30 | 0 | 1 hr | 1 | 0: Environment Setup |  | Attended CSIS 4495 Lesson 4 class; individual check-in with instructor; received feedback on project approach
2026-01-30 | 0 | 10 min | 0.17 | 0: Environment Setup | 0.5 | Created Streamlit Cloud account; connected with GitHub for deployment
2026-01-30 | 0 | 5 min | 0.08 | 0: Environment Setup | 0.6 | Created Python virtual environment (venv) for isolated project dependencies
2026-01-30 | 0 | 15 min | 0.25 | 0: Environment Setup | 0.7 | Installed packages: streamlit, openai, pandas, scikit-learn, plotly, folium, python-dotenv, numpy, nltk, sqlalchemy, spacy
2026-01-30 | 0 | 5 min | 0.08 | 0: Environment Setup | 0.8 | Ran 'streamlit hello' to verify Streamlit installation; demo app loaded successfully at localhost:8501
2026-01-30 | 0 | 10 min | 0.17 | 0: Environment Setup | 0.9 | Created requirements.txt using pip freeze; removed spacy model reference for clean deployment
2026-01-31 | 1 | 25 min | 0.42 | Learning & Research | L2 | Udemy Streamlit ML Deployment - Lesson 2: Installation and Setup (virtual environments, Python 3.8-3.12, streamlit hello)
2026-01-31 | 1 | 35 min | 0.58 | Learning & Research | L3 | Udemy Streamlit ML Deployment - Lesson 3: Overview of Streamlit (data flow concept, caching preview, key features)
2026-01-31 | 1 | 30 min | 0.5 | Learning & Research | L4 | Udemy Streamlit ML Deployment - Lesson 4: Creating Basic Streamlit App (main.py, st.text, auto-reload workflow)
2026-02-01 | 1 | 15 min | 0.25 | Learning & Research | L5 | Udemy Streamlit ML Deployment - Lesson 5: Text Elements (st.title, st.header, st.markdown, st.code, st.latex)
2026-02-01 | 1 | 20 min | 0.33 | Learning & Research | L6 | Udemy Streamlit ML Deployment - Lesson 6: Data Display Elements (st.dataframe, st.table, st.metric for KPIs)
2026-02-01 | 1 | 20 min | 0.33 | Learning & Research | L7 | Udemy Streamlit ML Deployment - Lesson 7: Charting Elements (st.line_chart, st.bar_chart, st.area_chart, st.map)
2026-02-01 | 1 | 25 min | 0.42 | Learning & Research | L8-9 | Udemy Streamlit ML Deployment - Lessons 8-9: Input Widgets (st.button, st.checkbox, st.radio, st.selectbox, st.slider)
2026-02-01 | 1 | 15 min | 0.25 | Learning & Research | L10 | Udemy Streamlit ML Deployment - Lesson 10: Forms (st.form, form_submit_button, batch submissions)
2026-02-01 | 1 | 15 min | 0.25 | Learning & Research | L11 | Udemy Streamlit ML Deployment - Lesson 11: Layout Elements (st.sidebar, st.columns, st.tabs, st.expander)
2026-02-01 | 1 | 40 min | 0.67 | Learning & Research | L12-13 | Udemy Streamlit ML Deployment - Lessons 12-13: Capstone (Canada population trend dashboard with forms, tabs, metrics, matplotlib)
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.1 | Create Mockup 1a - Login page design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.2 | Create Mockup 1b - Register page with health profile using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.3 | Create Mockup 2a - Home Dashboard design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.4 | Create Mockup 2b - Facility Finder page design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.5 | Create Mockup 2c - Health Library page design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.6 | Create Mockup 3 - Chatbot Interface design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.7 | Create Mockup 4 - My Dashboard (Personal) design using UX Pilot
2026-02-01 | Sprint 1 | 20 min | 0.33 | 1A: UI Mockups | 1A.8 | Create Mockup 5 - System Analytics page design using UX Pilot
2026-02-01 | Sprint 1 | 10 min | 0.17 | 1A: UI Mockups | 1A.9 | Organize all mockup files in Misc/design/ folder
2026-02-01 | Sprint 1 | 15 min | 0.25 | 1B: Project Structure | 1B.1 | Create folder structure (src/, pages/, components/, .streamlit/, data/)
2026-02-01 | Sprint 1 | 10 min | 0.17 | 1B: Project Structure | 1B.2 | Create .streamlit/config.toml with VCH theme colors (teal #006271, blue #0078AE)
2026-02-01 | Sprint 1 | 15 min | 0.25 | 1B: Project Structure | 1B.3 | Create empty placeholder files for all pages
2026-02-02 | Sprint 1 | 30 min | 0.5 | 1C: Database Setup | 1C.1 | Create components/database.py - Initialize SQLite database module using Claude Code
2026-02-02 | Sprint 1 | 30 min | 0.5 | 1C: Database Setup | 1C.2 | Create users table schema (id, name, email, password_hash, age, gender, region, health_conditions)
2026-02-02 | Sprint 1 | 30 min | 0.5 | 1C: Database Setup | 1C.3 | Create assessments table schema (id, user_id, symptoms, extracted_symptoms, urgency_level, recommendation)
2026-02-02 | Sprint 1 | 45 min | 0.75 | 1C: Database Setup | 1C.4 | Implement user CRUD functions (create_user, get_user_by_email, get_user_by_id, update_user, verify_user_exists)
2026-02-02 | Sprint 1 | 30 min | 0.5 | 1C: Database Setup | 1C.5 | Implement assessment CRUD functions (save_assessment, get_user_assessments, get_assessment_by_id, get_assessment_stats)
2026-02-02 | Sprint 1 | 20 min | 0.33 | 1C: Database Setup | 1C.6 | Test database with dummy data; Install SQLite Viewer VS Code extension; Verify tables
2026-02-02 | Sprint 1 | 5 min | 0.1 | 1C: Database Setup | 1C.7 | Git commit and push: 'Sprint 1C complete: Database setup with users and assessments tables'
2026-02-04 | Sprint 1 | 45 min | 0.75 | 1D: Authentication Feature | 1D.1 | Create components/auth.py (hash_password, verify_password functions using bcrypt)
2026-02-04 | Sprint 1 | 1 hr | 1 | 1D: Authentication Feature | 1D.2 | Create app.py with Login tab UI (email, password, remember me checkbox)
2026-02-04 | Sprint 1 | 1.5 hr | 1.5 | 1D: Authentication Feature | 1D.3 | Create app.py with Register tab UI (name, email, password, health profile, 10 health conditions)
2026-02-04 | Sprint 1 | 45 min | 0.75 | 1D: Authentication Feature | 1D.4 | Implement login logic (verify credentials, set session_state)
2026-02-05 | Sprint 1 | 45 min | 0.75 | 1D: Authentication Feature | 1D.5 | Implement register logic (validate, hash password, save to DB)
2026-02-05 | Sprint 1 | 15 min | 0.25 | 1D: Authentication Feature | 1D.6 | Add logout functionality (clear session and redirect to login)
2026-02-05 | Sprint 1 | 30 min | 0.5 | 1D: Authentication Feature | 1D.7 | Protect pages (redirect to login if not authenticated)
2026-02-05 | Sprint 1 | 30 min | 0.5 | 1D: Authentication Feature | 1D.8 | Test login/register/logout flow (9 test cases: registration, duplicate email, password/email validation, wrong password, logout, page protection, database verification); Clean up orphaned test data
2026-02-05 | Sprint 1 | 30 min | 0.5 | 1E: Basic Navigation | 1E.1 | Create pages/1_🏠_Home.py with welcome message
2026-02-05 | Sprint 1 | 10 min | 0.17 | 1E: Basic Navigation | 1E.2 | Create pages/2_💬_Symptom_Assessment.py (placeholder)
2026-02-05 | Sprint 1 | 10 min | 0.17 | 1E: Basic Navigation | 1E.3 | Create pages/3_📊_My_Dashboard.py (placeholder)
2026-02-05 | Sprint 1 | 10 min | 0.17 | 1E: Basic Navigation | 1E.4 | Create pages/4_🗺️_Facility_Finder.py (placeholder)
2026-02-05 | Sprint 1 | 10 min | 0.17 | 1E: Basic Navigation | 1E.5 | Create pages/5_📚_Health_Library.py (placeholder)
2026-02-05 | Sprint 1 | 10 min | 0.17 | 1E: Basic Navigation | 1E.6 | Create pages/6_📈_System_Analytics.py (placeholder)
2026-02-05 | Sprint 1 | 15 min | 0.25 | 1E: Basic Navigation | 1E.7 | Test navigation between all pages; Verify sidebar navigation works; Git commit and push
2026-02-06 | Sprint 2 | 10 min | 0.17 | 2A: Open AI Integration | 2A.1 | Create .streamlit/secrets.toml with OpenAI API key; secure storage configuration
2026-02-06 | Sprint 2 | 5 min | 0.08 | 2A: Open AI Integration | 2A.2 | Add secrets.toml to .gitignore to prevent accidental commit of API keys
2026-02-06 | Sprint 2 | 30 min | 0.5 | 2A: Open AI Integration | 2A.3 | Create components/openai_utils.py; set up OpenAI API wrapper functions with error handling
2026-02-06 | Sprint 2 | 1 hr | 1 | 2A: Open AI Integration | 2A.4 | Create extract_symptoms() function using GPT-4o-mini; NLP to extract structured symptoms from natural language user input
2026-02-06 | Sprint 2 | 20 min | 0.33 | 2A: Open AI Integration | 2A.5 | Test OpenAI API call with sample symptoms; verified extraction accuracy with test_openai.py
2026-02-07 | Sprint 2 | 30 min | 0.5 | 2B: Safety Layer - CTAS Rules | 2B.1 | Create components/rules.py; rule-based safety check module for emergency detection
2026-02-07 | Sprint 2 | 1 hr | 1 | 2B: Safety Layer - CTAS Rules | 2B.2 | Define CRITICAL_SYMPTOMS list; 10-15 emergency patterns based on CTAS Level 1-2 guidelines (chest pain, difficulty breathing, etc.)
2026-02-07 | Sprint 2 | 45 min | 0.75 | 2B: Safety Layer - CTAS Rules | 2B.3 | Create check_critical_symptoms() function; returns True with 911 warning if emergency keywords detected
2026-02-07 | Sprint 2 | 30 min | 0.5 | 2B: Safety Layer - CTAS Rules | 2B.4 | Test with emergency scenarios using test_rules.py; verified all critical symptom patterns caught correctly
2026-02-08 | Sprint 2 | 2 hr | 2 | 2C: ML Model Training | 2C.0 | Research prior ML algorithms used in healthcare triage/decision-making; documented findings in ML_Algorithm_Research.pdf
2026-02-08 | Sprint 2 | 30 min | 0.5 | 2C: ML Model Training | 2C.1 | Find and download Kaggle symptom-disease dataset (4920 rows, 41 diseases, 131 symptoms)
2026-02-08 | Sprint 2 | 45 min | 0.75 | 2C: ML Model Training | 2C.2 | Create notebooks/01_data_exploration.ipynb; explore dataset structure, class balance, symptom frequency, data quality issues
2026-02-08 | Sprint 2 | 1 hr | 1 | 2C: ML Model Training | 2C.3 | Create data/urgency_mapping.csv; map 41 diseases to 4 CTAS-aligned urgency levels (Emergency/Urgent/Routine/Self-Care)
2026-02-09 | Sprint 2 | 1 hr | 1 | 2C: ML Model Training | 2C.4 | Create components/train_model.py; 7-step pipeline (load, preprocess, one-hot encode, split, train, evaluate, save)
2026-02-09 | Sprint 2 | 1 hr | 1 | 2C: ML Model Training | 2C.5 | Create notebooks/02_train_model.ipynb; document training process with visualizations (confusion matrix, feature importance, F1 scores)
2026-02-09 | Sprint 2 | 2 hr | 2 | 2C: ML Model Training | 2C.6 | Train Random Forest classifier (100 trees, balanced weights, severity-weighted features); achieved 100% accuracy on test set
2026-02-09 | Sprint 2 | 30 min | 0.5 | 2C: ML Model Training | 2C.7 | Evaluate model accuracy; classification report, confusion matrix heatmap; all 41 diseases F1=1.00; documented 70% confidence threshold
2026-02-09 | Sprint 2 | 15 min | 0.25 | 2C: ML Model Training | 2C.8 | Save model.pkl (6.82 MB) and model_metadata.json to Implementation/models/; verified with test_predict.py
2026-02-10 | Sprint 2 | 1 hr | 1 | 2D: Chatbot UI + Integration | 2D.1 | Create components/chatbot.py using Claude Code; 3-layer assessment pipeline (OpenAI extraction → CTAS safety rules → ML classification) with fallback logic
2026-02-10 | Sprint 2 | 1.5 hr | 1.5 | 2D: Chatbot UI + Integration | 2D.2 | Build chat UI using st.chat_message and st.chat_input; assistant/user message styling; chat container layout matching mockup design
2026-02-10 | Sprint 2 | 20 min | 0.33 | 2D: Chatbot UI + Integration | 2D.3 | Add important disclaimer warning banner at top of Symptom Assessment page (not a substitute for medical advice, call 911 for emergencies)
2026-02-10 | Sprint 2 | 45 min | 0.75 | 2D: Chatbot UI + Integration | 2D.4 | Implement chat history persistence using st.session_state; messages survive page interactions; chat replay on rerun; Clear Chat button in sidebar
2026-02-10 | Sprint 2 | 2 hr | 2 | 2D: Chatbot UI + Integration | 2D.5 | Integrate full 3-layer assessment pipeline: OpenAI GPT-4o-mini extracts symptoms → CTAS safety rules check for emergencies → ML Random Forest classifies disease with urgency mapping; 70% confidence threshold triggers OpenAI fallback
2026-02-11 | Sprint 2 | 1 hr | 1 | 2D: Chatbot UI + Integration | 2D.6 | Create color-coded urgency badges using HTML/CSS: Emergency (red), Urgent (orange), Routine (yellow), Self-Care (green); styled inline badges with rounded corners
2026-02-11 | Sprint 2 | 45 min | 0.75 | 2D: Chatbot UI + Integration | 2D.7 | Add recommendation explanation text for each urgency level; Emergency shows 911/crisis line, Urgent shows 24hr care advice, Routine shows doctor visit guidance, Self-Care shows home remedies
2026-02-11 | Sprint 2 | 30 min | 0.5 | 2D: Chatbot UI + Integration | 2D.8 | Add BC Health Resources section: HealthLink BC (Call 8-1-1, free 24/7 health advice) and Facility Finder page reference; displayed after every assessment result
2026-02-11 | Sprint 2 | 45 min | 0.75 | 2D: Chatbot UI + Integration | 2D.9 | Add Save Assessment button that stores assessment to SQLite database (user_id, symptoms, extracted_symptoms, predicted_condition, confidence, urgency_level, recommendation); verified save with SQLite Viewer
2026-02-11 | Sprint 2 | 15 min | 0.25 | 2D: Chatbot UI + Integration | 2D.11a | Test 7-8: Mental health crisis → Emergency via CTAS safety rules (CTAS Level 2, matched 'suicidal'); 'my stomach hurts' → OpenAI fallback → Routine; both saved to database
2026-02-11 | Sprint 2 | 15 min | 0.25 | 2D: Chatbot UI + Integration | 2D.11b | Test 9a-9b: 'What's the weather today?' → correctly rejected as non-symptom input; 'stomach hurts + fever' follow-up → OpenAI fallback → Routine with escalation warnings
2026-02-11 | Sprint 2 | 15 min | 0.25 | 2D: Chatbot UI + Integration | 2D.11c | Test 10: 'runny nose and sneezing' → discovered bug: OpenAI fallback always defaulted urgency to Routine regardless of actual assessment; identified root cause in chatbot.py fallback logic
2026-02-11 | Sprint 2 | 30 min | 0.5 | 2D: Chatbot UI + Integration | BugFix | Fix critical bug: OpenAI fallback urgency classification now asks OpenAI to classify urgency (Emergency/Urgent/Routine/Self-Care) and parses response instead of hardcoding 'Routine'; verified fix with re-tests
2026-02-11 | Sprint 2 | 20 min | 0.33 | 2D: Chatbot UI + Integration | 2D.11d | Test 11: 'high fever, chills, sweating, vomiting, nausea, headache, muscle pain' → ML Model predicted Malaria (100% confidence) → Urgent; 7 symptoms matched ML feature names correctly
2026-02-11 | Sprint 2 | 15 min | 0.25 | 2D: Chatbot UI + Integration | 2D.11e | Tests 12a-c: Acne (skin rash, pimples, blackheads → 100% ML confidence → Self-Care); Allergy (itching, sneezing, shivering → 78% → Self-Care); Fungal infection (itching, rash, patches → 100% → Self-Care)
2026-02-11 | Sprint 2 | 20 min | 0.33 | 2D: Chatbot UI + Integration | UI-1 | Add personalized greeting: chatbot welcomes user by name from session state ('Hello [name]! I'm here to help assess your symptoms...'); no Save button on greeting message
2026-02-11 | Sprint 2 | 30 min | 0.5 | 2D: Chatbot UI + Integration | UI-2 | Add Urgency Level Guide reference card below BC Health Resources; 2x2 grid layout matching mockup (Emergency—Call 911 ¦ Urgent—ED/Urgent Care ¦ Routine—Walk-in/Doctor ¦ Self-Care—Home care); displayed on all result types
2026-02-11 | Sprint 2 | 10 min | 0.17 | 2D: Chatbot UI + Integration | 2D.11f | Test 13: 'severe chest pain can't breathe' → Emergency via CTAS rules; verified Urgency Level Guide now appears on Emergency results too; all 4 urgency levels confirmed working
2026-02-11 | Sprint 2 | 10 min | 0.17 | 2D: Chatbot UI + Integration | GIT-1 | Git commit: 'Add personalized greeting, urgency level guide (2x2 grid), and fix OpenAI fallback urgency classification'
2026-02-12 | Sprint 2 | 30 min | 0.5 | 2D: Chatbot UI + Integration | UI-3 | Design app logo using Google Gemini AI: BC mountain peaks + maple leaf + chat bubble + health cross; selected from 4 generated variations; created white version for teal banner and amber/gold version as primary
2026-02-12 | Sprint 2 | 15 min | 0.25 | 2D: Chatbot UI + Integration | UI-4 | Logo processing: crop Gemini watermark using Paint, resize to 200px for web optimization, create amber/gold (#F2A900) background variant for teal banner contrast
2026-02-12 | Sprint 2 | 1 hr | 1 | 2D: Chatbot UI + Integration | UI-5 | Create full-width teal (#006271) banner header across all pages using components/header.py; logo + 'BC Health Platform' on left, 'User: [name]' + Logout button on right; base64 logo embedding; position:fixed with z-index:999
2026-02-12 | Sprint 2 | 30 min | 0.5 | 2D: Chatbot UI + Integration | UI-6 | Fix CSS double-brace bug in header.py: _BANNER_CSS extracted from f-string had {{ }} escaping that broke all CSS rules; replaced with single braces; banner and sidebar offsets now render correctly
2026-02-12 | Sprint 2 | 45 min | 0.75 | 2D: Chatbot UI + Integration | UI-7 | Sidebar styling overhaul: bold darker text (#1a1a1a, font-weight:600), active tab teal (#006271) background with white text, monochrome icons via CSS grayscale filter, hide 'app' label; applied via inject_global_css()
2026-02-12 | Sprint 2 | 30 min | 0.5 | 2D: Chatbot UI + Integration | UI-8 | Hide sidebar on login page (CSS display:none + initial_sidebar_state=collapsed); fix logout redirect using st.switch_page('app.py') instead of st.rerun(); auto-redirect unauthenticated users to login
2026-02-12 | Sprint 2 | 30 min | 0.5 | 2D: Chatbot UI + Integration | UI-9 | Fix sidebar not visible after login: CSS specificity issue where hide_sidebar CSS overrode show rules; added explicit display:block !important with visibility/width overrides in authenticated banner CSS
2026-02-12 | Sprint 2 | 20 min | 0.33 | 2D: Chatbot UI + Integration | UI-10 | Replace default icons with custom logo on login page and authenticated landing page using base64 embedding; rename Symptom Assessment page title to 'Symptom Assessment Chatbot'
2026-02-12 | Sprint 2 | 15 min | 0.25 | 2D: Chatbot UI + Integration | 2D.12 | Git commits: 'Sprint 2D complete - Chatbot MVP with 3-layer assessment, banner, sidebar styling'; 'UI polish - custom logo, rename page, sidebar and banner fixes'; pushed to GitHub
2026-02-13 | Sprint 2 | 4 hr | 4 | 6: Documentation + Submission |  | Mid-term Report Writing
2026-02-13 | Sprint 2 | 2 hr | 2 | 6: Documentation + Submission |  | Mid-term Video Demonstration
2026-02-25 | Sprint 3 | 1 hr | 1 | 3A: Home Dashboard | 3A | Post-cruise return: Reviewed Sprint 3 roadmap tracker, organized project files and mockups into consolidated project workspace
2026-02-25 | Sprint 3 | 30 min | 0.5 | 3A: Home Dashboard | 3A | Studied existing 1_Home.py placeholder code, compared against UI mockup, identified all sections needing rebuild
2026-02-25 | Sprint 3 | 1 hr | 1 | 3A: Home Dashboard | 3A | Rebuilt Home page Welcome Header section with personalized greeting using session_state username, added health overview subtitle
2026-02-26 | Sprint 3 | 45 min | 0.75 | 3A: Home Dashboard | 3A | Created Quick Actions row (3 styled cards with icons: Check Symptoms, Find Facility, Health Info) with st.page_link() navigation
2026-02-26 | Sprint 3 | 1 hr | 1 | 3A: Home Dashboard | 3A | Created My Health Summary card querying SQLite database via get_assessment_stats() - displays total assessments, last check relative time, most common symptom with percentage
2026-02-26 | Sprint 3 | 45 min | 0.75 | 3A: Home Dashboard | 3A | Created Recent Activity list showing 3 most recent assessments from database with color-coded urgency dots (green/yellow/red)
2026-02-27 | Sprint 3 | 30 min | 0.5 | 3A: Home Dashboard | 3A | Added BC Health Tip of the Day banner with rotating BC-specific health tips and Find Nearest Pharmacy navigation button
2026-02-27 | Sprint 3 | 30 min | 0.5 | 3A: Home Dashboard | 3A | Added most_common_symptom_count to get_assessment_stats() in database.py for percentage calculation (backward-compatible change)
2026-02-27 | Sprint 3 | 30 min | 0.5 | 3A: Home Dashboard | 3A | Verified all dashboard data against SQLite database using Python queries - confirmed 33 assessments, Chest pain 33%, recent activity entries all match live data
2026-02-27 | Sprint 3 | 15 min | 0.25 | 3A: Home Dashboard | 3A | Git commit - 'Sprint 3A: Rebuild Home Dashboard to match UI mockup'
2026-02-28 | Sprint 3 | 30 min | 0.5 | 3B: My Dashboard - Personal Analytics | 3B | Studied My Personal Health Dashboard mockup (2 pages), identified 5 sections: stat cards, trend chart, symptoms breakdown, assessment history table, date filter
2026-02-28 | Sprint 3 | 1.5 hr | 1.5 | 3B: My Dashboard - Personal Analytics | 3B | Built dashboard layout with 4 stat summary cards (Total Checks, This Month, Most Common, Avg Urgency) with colored icon boxes and status indicators
2026-03-01 | Sprint 3 | 1.5 hr | 1.5 | 3B: My Dashboard - Personal Analytics | 3B | Created Plotly filled area chart for Symptom Trends Over Time - grouped assessments by month, teal color scheme, responsive layout with export_plotly_chart()
2026-03-01 | Sprint 3 | 1 hr | 1 | 3B: My Dashboard - Personal Analytics | 3B | Created Plotly donut pie chart for Symptoms Breakdown - shows distribution of primary symptoms with percentages, rare symptoms grouped as Other
2026-03-01 | Sprint 3 | 1 hr | 1 | 3B: My Dashboard - Personal Analytics | 3B | Created Assessment History HTML table with styled colored badges (green Home Care, yellow Walk-in Clinic, orange Urgent Care, red Emergency)
2026-03-02 | Sprint 3 | 45 min | 0.75 | 3B: My Dashboard - Personal Analytics | 3B | Implemented date filter dropdown (All Time, Last 6 Months, Last 3 Months, Last Year) that filters all dashboard sections simultaneously
2026-03-02 | Sprint 3 | 45 min | 0.75 | 3B: My Dashboard - Personal Analytics | 3B | Fixed UI issues - Plotly X-axis tick intervals (dtick=5), donut chart label clipping (moved labels inside slices with legend below), button styling for Export Report and New Assessment
2026-03-02 | Sprint 3 | 30 min | 0.5 | 3B: My Dashboard - Personal Analytics | 3B | Automated data verification against SQLite - confirmed all 4 stat cards, trend chart, donut chart percentages, and history table entries match real database values
2026-03-02 | Sprint 3 | 15 min | 0.25 | 3B: My Dashboard - Personal Analytics | 3B | Git commit - 'Sprint 3B: Rebuild My Dashboard with Plotly charts, date filter, and live data'
2026-03-02 | Sprint 3 | 15 min | 0.25 | 3B: My Dashboard - Personal Analytics | 3B | Added auto-redirect in app.py to route users to Home Dashboard after login instead of showing old placeholder page; Git commit
2026-03-02 | Sprint 3 | 45 min | 0.75 | Learning & Research |  | Researched agentic AI frameworks in healthcare triage (reviewed Thamma 2025, Wang et al. 2024); Evaluated feasibility for project integration
2026-03-02 | Sprint 3 | 45 min | 0.75 | 6: Documentation + Submission |  | Updated work log, prepared Progress Report 2, updated task tracker with Sprint 3A and 3B completion status
TOTAL HOURS |  |  |  | 101.85

## Dashboard
PROJECT PROGRESS DASHBOARD
SPRINT PROGRESS SUMMARY
Sprint | Phase Name | Target Hours | Actual Hours | % Complete
0 | Environment Setup | 5 | 11.85 | 100%
1 | Basic App Structure | 15 | 14.26 | 95.07%
2 | Symptom Chatbot | 25 | 29.99 | 100%
3 | Features 3A-3D | 20 | 6.75 | 33.75%
4 | System Analytics | 20 | 0 | 0%
5 | Deployment & Testing | 15 | 0 | 0%
6 | Documentation + Submission | 18 | 13.25 | 73.61%
TOTAL |  | 118 | 76.1 | 64.49%
GANTT CHART - PROJECT TIMELINE
Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
| Jan 27 | Feb 3 | Feb 10 | Feb 17 | Feb 24 | Mar 3 | Mar 10 | Mar 17 | Mar 24 | Mar 31 | Apr 7 | Apr 14 | Apr 21
Sprint 0: Environment Setup | bar: Jan 27 to Feb 3
Sprint 1: Basic App Structure | bar: Jan 27 to Feb 10
1A: UI Mockups | bar: Feb 3 to Feb 17
1B: Project Structure | bar: Feb 3 to Feb 10
1C: Database Setup | bar: Feb 3 to Feb 17
1D: Authentication Feature | bar: Feb 3 to Feb 17
1E: Basic Navigation | bar: Feb 10; Feb 24 to Mar 3
Sprint 2: Symptom Chatbot | bar: Feb 10 to Feb 24
2A: Open AI Integration | bar: Feb 10 to Mar 3
2B: Safety Layer - CTAS Rules | bar: Feb 17; Mar 3
2C: ML Model Training | bar: Feb 17 to Feb 24; Mar 10 to Mar 17
2D: Chatbot UI + Integration | bar: Feb 24; Mar 10
Sprint 3: Features 3A-3D | bar: Feb 24 to Mar 17
3A: Home Dashboard | bar: Feb 24 to Mar 3; Mar 17
3B: My Dashboard - Personal Analytics | bar: Mar 3; Mar 24 to Mar 31
3C: Facility Finder | bar: Mar 3 to Mar 10; Mar 24
3D: Health Education Library | bar: Mar 10; Mar 24 to Mar 31
3E: Multi-Turn Chatbot Enhancement | bar: Mar 10; Mar 24 to Mar 31
Sprint 4: System Analytics | bar: Mar 10 to Mar 31
4A: System Analytics Data | bar: Feb 24; Mar 10 to Mar 17
4B: System Analytics Dashboard | bar: Mar 17 to Mar 24; Apr 21
Sprint 5: Deployment & Testing | bar: Mar 24 to Apr 7
5A: Deployment | bar: Mar 24 to Mar 31
5B: Testing | bar: Mar 31 to Apr 7
Sprint 6: Documentation | bar: Apr 7 to Apr 21
Category | Jan 27: Hours
HOURS BY CATEGORY
Category | Jan 27: Hours
0: Environment Setup | Jan 27: 11.85
1A: UI Mockups | Jan 27: 2.81
1B: Project Structure | Jan 27: 0.67
1C: Database Setup | Jan 27: 3.18
1D: Authentication Feature | Jan 27: 6
1E: Basic Navigation | Jan 27: 1.6
2A: Open AI Integration | Jan 27: 2.08
2B: Safety Layer - CTAS Rules | Jan 27: 2.75
2C: ML Model Training | Jan 27: 9
2D: Chatbot UI + Integration | Jan 27: 16.16
3A: Home Dashboard | Jan 27: 6.75
3B: My Dashboard - Personal Analytics | Jan 27: 0
3C: Facility Finder | Jan 27: 0
3D: Health Education Library | Jan 27: 0
4A: System Analytics Data | Jan 27: 0
4B: System Analytics Dashboard | Jan 27: 0
5A: Deployment | Jan 27: 0
5B: Testing | Jan 27: 0
6: Documentation + Submission | Jan 27: 13.25
Learning & Research | Jan 27: 17.75
Proof of Concept | Jan 27: 0
TOTAL | Jan 27: 93.85

## Categories
Category Reference
Category | Sprint | Description
0: Environment Setup | 0 | Python, VS Code, GitHub, OpenAI API, Streamlit Cloud setup
1A: UI Mockups | 1 | Create UI mockups for all pages using UX Pilot
1B: Project Structure | 1 | Create folder structure, config.toml, placeholder files
1C: Database Setup | 1 | SQLite database, users/assessments tables, CRUD functions
1D: Authentication Feature | 1 | Login, register, logout, session management with bcrypt
1E: Basic Navigation | 1 | Multi-page navigation, sidebar, page routing
2A: Open AI Integration | 2 | OpenAI API setup, symptom extraction prompts
2B: Safety Layer - CTAS Rules | 2 | Rule-based critical symptom detection (CTAS guidelines)
2C: ML Model Training | 2 | Kaggle data, Random Forest training, model.pkl
2D: Chatbot UI + Integration | 2 | Chat interface, session state, urgency display, integration
3A: Home Dashboard | 3 | Home page with welcome message, quick stats, navigation cards
3B: My Dashboard - Personal Analytics | 3
3C: Facility Finder | 3 | BC facilities data, Folium map, filters by region/type
3D: Health Education Library | 3 | Health topics JSON, search, topic cards, resources
4A: System Analytics Data | 4 | Generate 5000 synthetic records, seasonal patterns
4B: System Analytics Dashboard | 4 | K-Means clustering, anomaly detection, forecasting
5A: Deployment | 5 | Streamlit Cloud deployment, secrets config, live testing
5B: Testing | 5 | Test scenarios, user feedback, edge cases, disclaimers
6: Documentation + Submission | 6 | Final report, demo video, presentation, submission
Learning & Research | - | Udemy courses, tutorials, documentation, self-study
Proof of Concept | - | Code experiments, feature demos, testing feasibility